## 1. INSTRUCTIONS
INSTRUCTIONS
This is the first of five sheets in this Excel workbook. This first sheet contains instructions for completing the tracker, the second sheet contains the fillable project tracker sheet. The third sheet contains the fillable financial summary sheet, and the fourth and fifth sheets contain examples of the tracker and project summary.
1) Open the "PROJECTS" worksheet (second tab) highlighted in blue and complete the following: a) This sheet is prepopulated with information from the state’s previously submitted Project Trackers (e.g. 20XX), as well as information from CMS Location on recently approved projects. Review the "prepopulated projects" for accuracy and provide updates, as necessary. Please specify any changes in Column M. Additionally, states are required to provide project results in Column J, see below for directions. b) Add any missing projects on a new row and complete all required fields for the "added projects".
Tracker Calendar Year Enter the relevant year. This field will remain highlighted (yellow) until year is entered.
State (Column A) Select state abbreviation from the drop down.
CMS Long-Term Care Branch (Column B) Field will auto-populate when state is selected in Column A.
Unique Identifier (Column C) This field should only be populated with the identifier provided by the CMS Location.
Project Start Date (Column D) Enter the start date of the project (i.e., the date that funding started). DO NOT enter the date the project was approved for funding. The project may have been approved months before funding began; only enter the date when the funding officially started. Please follow the format (MM/DD/YYYY). Example: 06/10/20XX. If the specific date is not known, use the first of the month: 06/01/20XX.
Project End Date (Column E) Enter the end date of the project. Whenever possible, please include specific dates, not just the month and year. Please follow the format (MM/DD/YYYY). Example: 09/25/20XX. If the specific date is not known, use the first of the month: 9/01/20XX.
Total Amount of CMP Funds Approved for this Project (Column F) Enter the total amount from the CMS project approval letter.
Project Title (Column G) Enter the Project Title from the CMS project approval letter.
Project Summary (Column H) The project summary should include a) specific purpose of the project, b) description of what the project will achieve (include the project’s quantifiable goal(s) and/or objective(s)), c) explanation of how the project will benefit nursing home residents, d) benefit to the nursing homes, e) target audiences beyond nursing home residents, if applicable.
Funded Entities (Column I) a) For prepopulated projects, this field is unlocked for editing. Please edit, as necessary and add a note in Column M indicating that a change has been made. b) For added projects, list each entity that will directly receive CMP funds for this project (i.e., if funds are being given directly to a nursing home, or non-nursing home entity such as an individual consultant, vendor, or academic institution, please list the name of the entity). DO NOT include the names of subcontracted entities.
Results/Outcomes of the Project (Column J) a) For prepopulated projects, this field is unlocked for editing. Please edit as necessary, and add a note in Column M indicating that a change has been made. Per CMS regulation, final project results must be reported annually for all projects that have been completed. Interim project results must be entered for all ongoing projects. b) For all projects, including added projects, describe the project's interim or final results and outcomes of the project. Include a brief summary of the specific goals that were met/not met, as well as any other benefits resulting from the project. Reference quantitative measures that reflect the goals of the project. If the project began implementation six months or less at the time of the Project Tracker submission, "Interim results not yet available" may be entered. c) If the project has concluded and the State is awaiting the final project results, interim results should be entered into the tracker. Example: Project ABC recruited 50 nursing homes to engage in training for the ABC program to improve resident communication and social connectedness. The project outcomes show a 10% reduction in residents exhibiting signs or symptoms of depression, challenging behaviors, and use of antipsychotic medication as well as a 20% in enjoyment of activities and social interaction.
Total Amount of CMP Funds Expended During the Calendar Year (Column K) Enter the total amount spent on this project during the calendar year. If this is a multi-year project or a project that is one year or less but spans multiple years, please enter the funds that were used during calendar year.
Notes (Column L) Please use this column to provide any relevant information to the CMPRP Team. Information provided in this column will not be included in the final Project Tracker on the CMPRP webpage.
2) Open the "FINANCIAL_SUMMARY” worksheet (third tab) highlighted in orange and complete the following:
a) The state must add information to all six highlighted (yellow) fields on this tab. Failure to provide this information will result in the file being returned to the state. If the total amount is zero, enter "$0." b) Update the relevant year (20XX) in the header row. See tab 5 for Example Financial Summary sheet.
Tracker Calendar Year Enter the relevant year. This field will remain highlighted until year is entered.
State (Column A) Select state abbreviation.
CMP Funds Balance as of January 1, 20XX (Obligated and Available) (Column B) Enter the amount that was obligated and available for the state at the start of the tracker calendar year (January 1).
CMP Funds Expended for Administrative Uses in CY20XX (Column C) Enter the actual amount of CMP funds expended for administrative uses during the calendar year. The amount entered must not exceed the amount allocated in your approved CMP Reinvestment State Plan. If the State expends more funds for administrative uses than was estimated in the relevant approved CMP Reinvestment State Plan, the State must submit the request to the CMPRP Team in an amended CMP Reinvestment State Plan for review. The amended plan must be approved by CMS prior to the state expending additional CMP funds for administrative uses.
CMP Funds Expended for Emergency Uses in CY20XX (Column D) Enter the actual amount of CMP funds expended for emergencies during the calendar year. States are required to reach out to their CMS Location to discuss use of funds as soon as the potential need arises. The State must seek CMS Location approval within 10 working days of the use of CMP emergency reserve funds for emergency use purposes such as the case of sudden nursing home relocations, natural disasters, or similar emergencies.
CMP Funds Added in CY20XX (Column F) Enter the actual amount of CMP funds that were added to the state's total balance during the calendar year. Note that the state was required to report the anticipated or project amount of CMP funds returned to the state during the calendar year as part of the State Plan submission process. This amount should reflect the actual amount of CMPs returned to the state.
CMP Funds Spent on CMP Projects in CY20XX (Column E) This cell will auto-populate with the total amount of funds listed in the projects from tab 3, "PROJECTS," Column L.
CMP Funds Balance of January 1, 20XX (Column G) This cell will auto-calculate by subtracting Column C (CMP Funds Expended for Administrative Uses), Column D (CMP Funds Expended for Emergency Uses), Column E (CMP Funds Spent on CMP Projects in CY20XX), and adding Column F (CMP Funds Added in CY20XX) to Column B (CMP Funds Balance as of January 1, 20XX).
3) Save and send the Project Tracker spreadsheet to the CMPRP mailbox (CMP-Info@cms.hhs.gov) by February 1st.
*Please feel free to reach out with any questions or concerns by contacting the mailbox at: CMP-Info@cms.hhs.gov

## 2. PROJECTS
FILLABLE TRACKER
Tracker Calendar Year (CY) |  | 2023 | 2022
State | CMS Long-Term Care Location | Unique Identifier | Project Start Date (Please review and edit the values in this field, as applicable) | Project End Date (Please review and edit the values in this field, as applicable) | Total Amount of CMP Funds Approved for this Project | Project Title | Project Summary (Please review and edit the values in this field, as applicable) a) Specific purpose of the project b) Description of what the project will achieve (include the project’s quantifiable goal(s) and/or objective(s)) c) Explanation of how the project will benefit nursing home (NH) residents d) Benefit to the nursing home (NH) e) Target audiences beyond NH residents, if applicable | Funded Entities (Please review and edit the values in this field, as applicable) | Results/Outcomes of the Project (Please review and edit the values in this field, as applicable) a) For prepopulated projects, this field is unlocked for editing. Per CMS regulation, final project results must be reported annually for all projects that have been completed. Interim project results must be entered for all ongoing projects. b) If the project began implementation six months or less at the time of the Project Tracker submission, "Interim results not yet available" may be entered. c) If the project has concluded and the State is awaiting the final project results, interim results should be entered into the tracker. | Total Amount of CMP Funds Expended on Projects During CY 2022 (Please review and edit the values in this field, as applicable) | Total Amount of CMP Funds Expended on Projects During CY 2023 (Please review and edit the values in this field, as applicable) | Notes
Mississippi | Atlanta | MS-0919-DHS-412 / 2019-04-MS-0911 | 2020-01-06 | 2023-01-31 | 140436 | Make “Diversicare” Great Again | Diversicare Healthcare Services requested funding to implement It's Never Too Late (iN2L) technology in three facilities. Each center's Administrator will manage the project's implementation and evaluation individually and provide progress reports to the Senior Administrator for oversight and assistance as needed. The project aims to reduce antipsychotics, antidepressants, and antianxiety classes closer to the national average of 7.2 percent over three years. | Diversicare Healthcare Services | With the use of the It's Never Too Late (iN2L) technology, Diversicare Healthcare Services were are able to pull up campfire scenes while the residents made s’mores and reminisced about their childhood to adulthood. They are able to have movie night with movie at the request of residents for their favorite movies. During Thanksgiving season the residents were able to watch the live Macy Thanksgiving Day parade and have dinner while listening to soothing music. Bingo was a big hit for the facility as well as the residents and hospice volunteers. The games alone for individual use helped with residents being bored, the therapeutic music for all occasions made for an awesome conversation during socials. The therapy team was also able to utilize the mobile device for therapy sessions. The project reported that iN2L has been a great addition to the lives it has touched. | 0 | 0
Mississippi | Atlanta | MS-0220-LTC-571 / 2020-04-MS-0219 | 2020-09-01 | 2023-08-31 | 378366 | Long-Term Care Resident Welfare (LTCRW), also known as It's Never Too Late (iN2L) Project | The Long-Term Care Resident Welfare (LTCRW) project, also known as It's Never Too Late (iN2L), aims to implement the iN2L system over a three-years term. The project provides nursing home residents in six Mississippi skilled nursing facilities (SNF) with access to person-centered recreation and leisure activities to improve the overall quality of life of nursing home residents. The project's goal is to establish an integrated and enriched activity program for residents in six nursing facilities. The goal is to increase group or one-on-one activity participation; customize personal "pages" and digital biographies reflecting the residents' preferences and interests; and it will also promote a greater number of staff or volunteer-facilitated Skype interactions with family and friends per month. These goals and objectives will be achieved over a 36-month term. The participating nursing homes are Hattiesburg Health and Rehabilitation, Forest Hill Nursing Center, Glen Oaks Nursing Center, Tunica County Health and Rehabilitation, Union County Health and Rehabilitation, and Quitman County Health and Rehabilitation. | Long-Term Care Management | Long-Term Care Resident Welfare's It's Never Too Late (iN2L) project goals were to train and provide resources to six nursing facilities with a purpose to improved the lives of residents through the use of technology, to promote group activities and stimulate cognitive functions. Interim results show five out of six facilities increased iN2L group application usage compared to the previous quarter. The Long-Term Care Management continues to utilize various strategies to utilize It's Never Too Late (IN2L) devices while facing several challenges in their facilities. They have continued to educate and encourage their residents on the benefits of using technology. The facility staff are actively engaging residents to embrace technology as a way to connect with family members and fellow residents. Long-Term Care Management's strategy for the last quarter was to continue encouraging residents to utilize IN2L's technology in order to increase peer interactions with the hope to increase individual tablet use and encourage their residents to reach out to their families more through Skype and Facetime. The last report that received by the State Agency (SA) was on 5/31/2023 for the months of January 2023 - March 2023. The SA has requested the final report; however, it has not yet been received. The project ended on 8/31/2023. | 0 | 172169.5
Mississippi | Atlanta | MS-0320-MSU-579 / 2020-04-MS-0229 | 2021-10-01 | 2024-09-20 | 360928 | Bingocize®: An Evidence-Based Health Promotion Program to Improve the Quality of Life of Mississippi Certified Nursing Facility Residents | The primary goal of the Bingocize® project is to use the Western Kentucky University (WKU) Center for Applied Science in Health Aging (CASHA) model to train 170 certified nursing facility (CNF) staff to implement the Bingocize® program in 24 CNFs across Mississippi within a three-year period. The secondary goal is to facilitate strong and long-term community partnerships between faculty (4) and students (200) at Mississippi State University and CNF staff. The purpose of the project is to provide CNF residents the opportunity to participate in a program capable of improving their quality of life in several ways. First, the exercise portion of the program will positively impact functional performance leading to maintenance in activities of daily living (ADLs) and reducing fall risk. Second, because the Bingocize® program is a group activity, the residents can engage socially and communicate with other residents, staff, university faculty, and students. Finally, residents will enjoy playing Bingocize® and winning prizes. | Mississippi State University | The Mississippi Bingocize® team has made strong and steady progress toward the Bingocize® project goals. This is the thirteenth quarterly report prepared for the Mississippi Division of Medicaid and Centers for Medicare and Medicaid Services (CMS) official review. As of March 31st, 2024, the team had trained 192 people and issued Bingocize® certificates, with 59 of them being certified nursing facilities (CNF) staff, 126 being university students who plan or are interested in working in healthcare or geriatric nursing, and six (6) being university faculty who teach gerontology relevant courses or work with geriatric populations. Every Friday at Dungan Memorial Home, an undergraduate student worker visits to assist with Bingocize®. Despite a class time conflict, a volunteer from Mississippi State University (MSU) is able to help. Every Thursday afternoon at Louisville Healthcare, LLC, two undergraduate students consistently assist with Bingocize® activities, with five to eight Mississippi State University (MSU) undergraduates volunteering each session. At least 15 residents participate in Bingocize®. At Trinity Place Retirement Community, two undergraduate students were scheduled to assist with Bingocize® activities in March. However, the roof of the activity center collapsed, and the Bingocize® activities have been suspended. Project activities are planned to resume at Trinity Place Retirement Community in May. Final project results are pending. | 62009.71 | 46042.99 | Column F has been updated to reflect the correct award amount of $360,928.00.
Mississippi | Atlanta | MS-0620-LTCC-625 / 2020-04-MS-0527 | 2020-09-14 | 2023-09-14 | 738750 | SNFClinic | The primary goal and purpose of the SNFClinic project is to provide comprehensive, accurate, and cost-effective tools to ensure skilled nursing facilities (SNFs) are providing high quality care to their residents. SNFClinic aims to assist the participating facility in the development of systems to demonstrate better pathways contributing to better resident satisfaction and outcomes, benefitting both residents and the facility through educational trainings for the enhancement of care delivery for the resident. Over a three-year term, the SNFClinic project aims to provide 25 Mississippi nursing homes with a CMS one or two-star quality rating with educational training and checklists designed to improve nursing staff performance. The project intends to show improving the quality of care that residents receive will also lead to an improvement in residents’ overall quality of life. The project aims to use the Minimum Data Set (MDS) to assess project success. | Long-Term Care Consultants | SNFClinic final outcome shows 24 participating skilled nursing facilities (SNFs) over a 3-year term were provided with computer technology related to staff training and resident care. Twenty-three (23) out of 24 facilities improved in almost half (48.88%) of its Minimum Data Set (MDS) quality measures that demonstrates that the project met its goal of improving the quality of person-centered care provided at facilities. 65% of the participating facilities improved both baseline and subsequent health inspection score by 57.42%. These results demonstrate that the project contributed to improved health inspection score outcomes, (reduction in Survey Deficiencies and Improvement in Scope and Severity of Tags). Upon conclusion of the project, 13 participating facilities chose to continue using SNFClinic as private payees. | 259350 | 165300
Mississippi | Atlanta | MS-0820-TMF-659 / 2020-04-MS-0820 | 2021-03-01 | 2023-02-28 | 563152.66 | Smile Proud: Improving Oral Health Among Mississippi Nursing Home Residents Project | The two-year Smile Proud Project aims to implement a comprehensive oral care training program in 60 skilled nursing facilities throughout Mississippi, focusing on facilities with a CMS one-or two-star quality rating. The program includes on-site staff education in oral care for nursing home residents and the creation of an oral health promotion toolkit. | TMF Health Quality Initiative | Smile Proud: Improving Oral Health Among Mississippi Nursing Home Residents project's goals: The Smile Proud Mississippi (MS) project began on March 1, 2021. They recruited 53 nursing homes through February 2023. Completed training 1 for 86 staff members in four nursing homes during Quarter 4, Year 2, for a total of 752 staff members in 51 nursing homes trained to date. Completed training 2 for 58 staff members in six nursing homes in Quarter 4, Year 2, for a total of 589 staff members in 50 nursing homes trained to date. Completed training 3 for 22 staff members in 12 nursing homes in Quarter 4, Year 2, for a total of 408 staff members in 50 nursing homes trained to date. Completed training 4 for 30 staff members in 16 nursing homes in Quarter 4, Year 2, for a total of 174 staff members in 50 nursing homes trained to date. Completed 13 Baseline Oral Health Activity forms that were returned to TMF after considerable outreach. 1,243 residents benefited from receiving oral care from staff who were trained in the proper procedure as well how to identify oral cancer during this quarter. In addition, the OHOAW (spell out) members developed a Statewide Sustainability Plan that lead to dental hygiene students doing a clinical rotation with nursing home residents. This especially benefit those with no or limited funding sources for oral care. | 278936.64 | 54538.36

## 3. FINANCIAL_SUMMARY
FILLABLE FINANCIAL SUMMARY TRACKER
Tracker Calendar Year (CY) |  | 2023 | 2024
State | CMP Funds Balance as of January 1, 2023 (Obligated & Available) | CMP Funds Expended for Administrative Uses in CY2023 | CMP Funds Expended for Emergency Uses in CY2023 | CMP Funds Spent on Projects in CY2023 | CMP Funds Added in CY2023 | CMP Funds Balance as of January 1, 2024
MS | 13302750.44 | 0 | 0 | 438050.85 | 1104072.51 | 13968772.1

## 4. EXAMPLE_PROJECTS
EXAMPLE FILLABLE TRACKER
Tracker Calendar Year (CY) |  | 2022 | 2021
State | CMS Long-Term Care Location | Unique Identifier | Project Start Date (Please review and edit the values in this field, as applicable) | Project End Date (Please review and edit the values in this field, as applicable) | Total Amount of CMP Funds Approved for this Project | Project Title | Project Summary (Please review and edit the values in this field, as applicable) a) Specific purpose of the project b) Description of what the project will achieve (include the project’s quantifiable goal(s) and/or objective(s)) c) Explanation of how the project will benefit nursing home (NH) residents d) Benefit to the nursing home (NH) e) Target audiences beyond NH residents, if applicable | Funded Entities (Please review and edit the values in this field, as applicable) | Results/Outcomes of the Project (Please review and edit the values in this field, as applicable) a) States should report preliminary (interim) results per the reporting requirements within the State’s approved relevant CMP Reinvestment State Plan. b) If the project is currently being implemented and no preliminary (interim) results are available, “Results Pending” should be entered into the results section. c) If the project has concluded and the State is awaiting the final project results, interim results should be entered into the tracker. | Total Amount of CMP Funds Expended on Projects During CY 2021 (Please review and edit the values in this field, as applicable) | Total Amount of CMP Funds Expended on Projects During CY 2022 (Please review and edit the values in this field, as applicable) | Notes
OH | Chicago | XXXX-OH-XXX | 2020-01-01 | 2020-12-31 | 50000 | TimeSlips Creative Storytelling | a) The purpose of this project is to improve communication and social connectedness for nursing home residents. b) TimeSlips Creative Storytelling will train and certify 50 nursing homes in improvisational storytelling. They will recruit and train facility staff, certify lead facilitators, and hold face-to-face and virtual coaching sessions for technical assistance. c) In addition to improving communication and social connectedness, the project aims to reduce challenging behaviors, reduce antipsychotic medications, and encourage positive engagement between staff and residents. d) 50 nursing homes in the state. | TimeSlips Creative Storytelling | TimeSlips recruited 50 nursing homes to engage in training for the Creative Storytelling program. Survey responses collected from all 50 nursing homes showed a 20% reduction in resident depression, irritability, and apathy as well as a 30% increase in enjoyment of activities and social interaction. A total of 49 testimonials detailing resident improvement in imagination/ creativity, community contribution, talking, and laughing serve as strong qualitative indicators of success. | 0 | 30000 | N/A

## 5. EXAMPLE_FINANCIAL SUMMARY
EXAMPLE FILLABLE FINANCIAL SUMMARY TRACKER
Tracker Calendar Year (CY) |  | 20XX | 20XX
State | CMP Funds Balance as of January 1, 20XX (Obligated & Available) | CMP Funds Expended for Administrative Uses in CY20XX | CMP Funds Expended for Emergency Uses in CY20XX | CMP Funds Spent on Projects in CY20XX | CMP Funds Added in CY20XX | CMP Funds Balance as of January 1, 20XX
Ohio | 40000 | 2000 | 3000 | 30000 | 6000 | 11000