## PPHR PPC
Mississippi Division of Medicaid
Quality Incentive Payment Program (QIPP)
Potentially Preventable Hospital Return (PPHR) and
Potentially Preventable Complications (PPC)
SFY 2026 Timeline
QUARTER ONE (September 2025 MHAP)
PPHR Report (Cycle 7) is based on January 1, 2023 - December 31, 2024 PPC Report (Cycle 5) is based on January 1, 2023 - December 31, 2024
DUE DATE | DAY | ACTION | DESCRIPTION
2025-07-14 | Monday | Myers and Stauffer to upload the PPHR and PPC Reports. QIPP Team to notify Hospitals and CCOs via Email. | Actual Day
2025-07-29 | Tuesday | QIPP Team to email Hospitals, who have yet to submit Attestations | Midpoint: 2nd Notice Reminders
2025-08-13 | Wednesday | Deadline. Last Day Hospitals may submit signed Attestations to DOM | Due Date: 30 calendar days after receipt to attest
2025-08-14 | Thursday | Designated Team Member to report attestations to QIPP Team | One business day after due date
2025-08-19 | Tuesday | CAP reminder email sent with email regarding PPHR and PPC Reports. | Midpoint: 15 calendar days before the CAP submission deadline
2025-09-02 | Tuesday | Deadline: CAP forms due back from those Hospitals required to submit. | CAP submission deadline
2025-09-03 | Wednesday | Designated Team Member to report CAP submissions to QIPP Team | One business day after due date
QUARTER TWO (December 2025 MHAP)
PPHR Report is based on April 1, 2023 - March 31, 2025 PPC Report is based on April 1, 2023 - March 31, 2025
DUE DATE | DAY | ACTION | DESCRIPTION
2025-10-06 | Monday | Myers and Stauffer to upload the PPHR and PPC Reports to SharePoint. QIPP Team to notify Hospitals via Email. | Actual Day
2025-10-20 | Monday | QIPP Team to email Hospitals, who have yet to submit Attestations | Midpoint: 2nd Notice Reminders
2025-11-05 | Wednesday | Deadline. Last Day Hospitals may submit signed Attestations to DOM | Due Date: 30 calendar days after receipt to attest
2025-11-06 | Thursday | Designated Team Member to report attestations to QIPP Team | One business day after due date
QUARTER THREE (March 2026 MHAP)
PPHR Report is based on July 1, 2023 - June 30, 2025 PPC Report is based on July 1, 2023 - June 30, 2025
DUE DATE | DAY | ACTION | DESCRIPTION
2026-01-07 | Wednesday | Myers and Stauffer to upload the PPHR and PPC Reports to SharePoint. QIPP Team to notify Hospitals via Email. | Actual Day
2026-01-21 | Wednesday | QIPP Team to email Hospitals, who have yet to submit Attestations | Midpoint: 2nd Notice Reminder
2026-02-09 | Monday | Deadline. Last Day Hospitals may submit signed Attestations to DOM | Due Date: 30 calendar days after receipt to attest
2026-02-10 | Tuesday | Designated Team Member to report attestations to QIPP Team | One business day after due date
QUARTER FOUR (June 2026 MHAP)
PPHR Report is based on October 1, 2023 - September 30, 2025 PPC Report is based on October 1, 2023 - September 30, 2025
DUE DATE | DAY | ACTION | DESCRIPTION
2026-04-06 | Monday | Myers and Stauffer to upload the PPHR and PPC Reports to SharePoint. QIPP Team to notify Hospitals via Email. | Actual Day
2026-04-20 | Monday | QIPP Team to email Hospitals, who have yet to submit Attestations | Midpoint: 2nd Notice Reminder
2026-05-06 | Wednesday | Deadline. Last Day Hospitals may submit signed Attestations to DOM | Due Date: 30 calendar days after receipt to attest
2026-05-07 | Thursday | Designated Team Member to report attestations to QIPP Team | One business day after due date

## AM-PPC
Mississippi Division of Medicaid
Quality Incentive Payment Program (QIPP)
Ambulatory Potentially Preventable Complications (AM-PPC)
SFY 2026 Timeline
QUARTER ONE (September 2025 MHAP)
AM-PPC Report (Cycle 2) is based on January 1, 2023 - December 31, 2024
DUE DATE | DAY | ACTION | DESCRIPTION
2025-07-30 | Wednesday | Myers and Stauffer to upload the AM-PPC Reports. QIPP Team to notify Hospitals and CCOs via Email. | Actual Day
2025-08-13 | Wednesday | QIPP Team to email Hospitals, who have yet to submit Attestations | Midpoint: 2nd Notice Reminders
2025-08-29 | Friday | Deadline. Last Day Hospitals may submit signed Attestations to DOM | Due Date: 30 calendar days after receipt to attest
2025-09-02 | Tuesday | Designated Team Member to report attestations to QIPP Team | One business day after due date
QUARTER TWO (December 2025 MHAP)
AM-PPC Report is based on April 1, 2023 - March 31, 2025
DUE DATE | DAY | ACTION | DESCRIPTION
2025-10-20 | Monday | Myers and Stauffer to upload the AM-PPC Reports. QIPP Team to notify Hospitals and CCOs via Email. | Actual Day
2025-11-03 | Monday | QIPP Team to email Hospitals, who have yet to submit Attestations | Midpoint: 2nd Notice Reminders
2025-11-19 | Wednesday | Deadline. Last Day Hospitals may submit signed Attestations to DOM | Due Date: 30 calendar days after receipt to attest
2025-11-20 | Thursday | Designated Team Member to report attestations to QIPP Team | One business day after due date
QUARTER THREE (March 2026 MHAP)
AM-PPC Report is based on July 1, 2023 - June 30, 2025
DUE DATE | DAY | ACTION | DESCRIPTION
2026-01-21 | Wednesday | Myers and Stauffer to upload the AM-PPC Reports. QIPP Team to notify Hospitals and CCOs via Email. | Actual Day
2026-02-04 | Wednesday | QIPP Team to email Hospitals, who have yet to submit Attestations | Midpoint: 2nd Notice Reminder
2026-02-20 | Friday | Deadline. Last Day Hospitals may submit signed Attestations to DOM | Due Date: 30 calendar days after receipt to attest
2026-02-23 | Monday | Designated Team Member to report attestations to QIPP Team | One business day after due date
QUARTER FOUR (June 2026 MHAP)
AM-PPC Report is based on October 1, 2023 - September 30, 2025
DUE DATE | DAY | ACTION | DESCRIPTION
2026-04-20 | Monday | Myers and Stauffer to upload the AM-PPC Reports. QIPP Team to notify Hospitals and CCOs via Email. | Actual Day
2026-05-04 | Monday | QIPP Team to email Hospitals, who have yet to submit Attestations | Midpoint: 2nd Notice Reminder
2026-05-20 | Wednesday | Deadline. Last Day Hospitals may submit signed Attestations to DOM | Due Date: 30 calendar days after receipt to attest
2026-05-21 | Thursday | Designated Team Member to report attestations to QIPP Team | One business day after due date